## Tracker
No | Topic | Description | Type (A/D/I) | Status | Responsible | Date Opened | Target Comp Date | Progress Updates/ Comments | Final Resolution | Date Closed
ADI-001 | Program | Create Github project for collaboration. | Action | Closed | Kiran | 2020-06-04 | 2020-06-05 |  | Project created on github https://github.com/kiranmak/pucsd-levelup | 2020-06-05
ADI-002 | Launch | Socialize the concept, scope and approach with 1994 Alumni Batch | Action | In Progress | Krishnan | 2020-06-19 | 2020-07-03 | Need to draft a communication on the overall plan and send it batch 94 whats app group as an FI
ADI-003 | Launch | Formalize launch concept and have next level actions to prepare content | Action | Open | ? | 2020-06-19
ADI-004 | Communication | Formalize communication channels to the following target groups:- 1. Students 2. Faculty 3. Alumni | Action | In Progress | Kavita | 2020-06-19 | 2020-07-15 | 26/June : Sent an email to Patil sir for guidance, will frame resolution based on response
ADI-005 | Problem-Solving | Finalize Course Syllubus / Structure | Action | In Progress | Kavita | 2020-06-19 | 2020-07-15
ADI-006 | Communication | The topic owners can reach out on an individual basis to alumni for engage them for support / volunteer | Decision | Closed |  | 2020-06-19 | 2020-06-19 |  |  | 2020-06-19
ADI-007 | Communication | Communicating broadly to the larger alumni - please wait for action item ADI-002 and ADI-004 to be completed with resolution | Decision | Closed |  | 2020-06-19 | 2020-06-19 |  |  | 2020-06-19
AD-008 | Program | Changed the Program Structure on github. Created folders for indvidual topic owners to for detailed content and execution plan update. The scope document should be limited now only to scope. | Information | Open | Kavita | 2020-06-26
ADI-009 | Hackathon | Need to finalize the coding language for the hackathon after checking with the faculty | Decision | Open | Krishnan | 2020-06-26 | 2020-07-10 | Plan is to use Python but we would like to check this with the faculty
ADI-010 | Communication | Need to get email ids of all the faculty members so that we can get contact them on a | Information | Open |  | 2020-06-27
ADI-011 | Hackathon | Finalize the hackathon platform | Decision | Open | Krishnan/Kiran | 2020-06-26 | 2020-07-10 | Looking at hackerrank to see if it meets all the requirements. Planning to do a dry run in next week's meeting
ADI-012 | Hackathon | Content, frequency and timelines for the coding challenges | Decision | In Progress | Krishnan/Kiran | 2020-06-26 | 2020-07-10 | Content - Plan to use pre-existing coding challenges available in hackerrank for the individual assignments. Will focus on open ended problems for the group hackathons. Duration: 24-48 hours during the weekend Frequency: a. Individual assignments - Once every 2 weeks b. Group hackathons - Once every month Schedule: a. Individual assignments from Aug 2020 b. Group assignments from Oct 2020 assuming students are back in the campus by then
ADI-013 | Hackathon | Incentives for the hackathons | Decision | Open |  | 2020-06-26 | 2020-07-10 | Possible options: 1. Cash/e-vouchers 2. Certificates from department 3. LinkedIn recommendations 4. Opportunity to present the solution to the dept
Note on D1: Action / Information / Decision

## Meta-Data
Type
Action
Decision
Information
Status
Open
In Progress
Closed
Deferred
Cancelled
Not Relevant